## Calvin Thang
To-do list
To be completed by: |  |  |  | Name: Calvin Thang
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Meeting 1 | 2021-03-04 | 2021-03-09 | N/A | 5 days | DONE
100% | First, finish the JDBC LinkedIn video course | 2021-03-08 | 2021-03-12 |  | 4 days
100% | Meeting 2 on Saturday | 2021-03-13 | 2021-03-13
100% | Code the JDBC in Java | 2021-03-13 | 2021-03-15 |  | 2 days
100% | Meeting 3 on Monday | 2021-03-22
100% | Create 20 propositions | 2021-03-19 | 2021-03-23
100% | Create 20 queries | 2021-03-19 | 2021-03-24
100% | Meeting 4 to select top 3 best propositions and top 3 worst propositions; thursday on 10:30 | 2021-03-25 | 2021-03-25
100% | Prioritize top 3 best propositions AND top 3 worst propositions | 2021-03-25 | 2021-03-25
100% | Review the team’s problems by simple, medium and complex | 2021-03-25 | 2021-03-25
100% | Create the diagrams for each proposition | 2021-03-22 | 2021-03-26
100% | Create the PowerPoint | 2021-03-25 | 2021-03-26
100% | Check over everything; Meeting 5 | 2021-03-26 | 2021-03-26
100% | Annotate the PowerPoint | 2021-03-25 | 2021-03-27
100% | Create the team’s problems by simple, medium and complex with regards to the JDBC | 2021-03-25 | 2021-03-27
100% | Create a voice video of the JDBC execution of the group’s three top queries from simple, medium and complex execution. | 2021-03-25 | 2021-03-27
100% | Create a VHDX file as a submission format with a directory structure | 2021-03-28 | 2021-03-28
100% | Submit | 2021-03-29 | 2021-03-29

## Hasnain Maqsood
To-do list
To be completed by: |  |  |  | Name: Hasnain Maqsood
Deadline: |  |  |  | Date:03/09/2021
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Meeting 1 | 2021-03-04 | 2021-03-09 | Finished by 03/09/2021 | 4
100% | Java JDBC library | 2021-03-09 | 2021-03-12 |  | 1
100% | Meeting 2 | 2021-03-13 | 2021-03-13 |  |  | Assign propositions to be brainstormed by MARCH 13 - 15
100% | Develop 20 propositions | 2021-03-20 |  |  |  | 5 simple, 8 medium and 7 complex(Not yet completed)
100% | Meeting 3 on Monday | 2021-03-22
100% | Prioritize top 3 best propositions AND top 3 worst propositions | 2021-03-22 | 2021-03-25
100% | Review the team’s problems by simple, medium and complex | 2021-03-25 | 2021-03-25
100% | Create the diagrams for each proposition | 2021-03-22 | 2021-03-26
100% | Create the PowerPoint | 2021-03-25 | 2021-03-26
100% | Check over everything; Meeting 5 | 2021-03-26 | 2021-03-26
100% | Annotate the PowerPoint | 2021-03-25 | 2021-03-27
100% | Create the team’s problems by simple, medium and complex with regards to the JDBC | 2021-03-25 | 2021-03-27
100% | Create a voice video of the JDBC execution of the group’s three top queries from simple, medium and complex execution. | 2021-03-25 | 2021-03-27
100% | Create a VHDX file as a submission format with a directory structure | 3//25/21 | 2021-03-28
100% | Submit | 2021-03-29 | 2021-03-29

## Alexander Perinetti
To-do list
To be completed by: |  |  |  | Name: Alexander Perinetti
Deadline: |  | 2021-03-29 |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Meeting 1 | 2021-03-04 | 2021-03-09 |  | 5 | Done
100% | JDBC - finish code | 2021-03-08 | 2021-03-12 |  | 4 | Done
100% | Meeting 2 | 2021-03-13 | 2021-03-13 |  | 1 | Done
100% | Make 20 propositions | 2021-03-13 | 2021-03-15 | 2021-03-23 | 10 | reprioritized to do JDBC and midterm
100% | Meeting 3 | 2021-03-22 | 2021-03-22 |  | 1 | Done
100% | pick top 3 and worst 3 queries | 2021-03-25 | 2021-03-26 |  | 1 | Done
100% | documentation | 2021-03-25 | 2021-03-25 |  | 1 | Done
100% | review teams top and bottom 3 queries | 2021-03-25 | 2021-03-26 |  | 1 | Done
100% | create diagrams | 2021-03-22 | 2021-03-25 |  | 3 | Done
100% | create powerpoint | 2021-03-25 | 2021-03-26 |  | 1 | Done
100% | annotate powerpoint | 2021-03-25 | 2021-03-26 |  | 1 | Done
100% | Choose team's top and worst 3 queries | 2021-03-25 | 2021-03-26 |  | 1 | Done
100% | do voice video JDBC | 2021-03-25 | 2021-03-26 |  | 1 | Done
100% | create vhdx and final review | 2021-03-25 | 2021-03-29 |  | 4 | Done
0%

## Joseph Shimonov
To-do list
To be completed by: |  |  |  | Name: Joseph Shimonov
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Meeting 1 | 2021-03-04 | 2021-03-09 | N/A | 5 days
100% | First, finish the JDBC LinkedIn video course | 2021-03-08 | 2021-03-12 |  | 4 days | Done
100% | Meeting 2 on Saturday | 2021-03-13 | 2021-03-13
100% | Code the JDBC in Java | 2021-03-13 | 2021-03-14 |  | 1 day | Done
100% | Meeting 3 on Monday | 2021-03-22
100% | Create 20 propositions | 2021-03-18 | 2021-03-26 |  | 8 days | Done
100% | Create 20 queries | 2021-03-18 | 2021-03-26 |  | 8 days | Done
100% | Meeting 4 to select top 3 best propositions and top 3 worst propositions; thursday on 10:30 | 2021-03-25 | 2021-03-25
100% | pick top 3 and worst 3 queries | 2021-03-25 | 2021-03-26 |  | 1 day | Done
100% | Create the diagrams for each proposition | 2021-03-24 | 2021-03-26 |  | 2 days | Done
100% | Create the PowerPoint | 2021-03-25 | 2021-03-26 |  | 1 day | Done
100% | Annotate the PowerPoint | 2021-03-25 | 2021-03-26 |  | 1 day | Done
100% | Create a voice video of the JDBC execution of the group’s three top queries from simple, medium and complex execution. | 2021-03-25 | 2021-03-29 |  | 2 days | Done
100% | Submit | 2021-03-29 | 2021-03-29 |  | 0 days | Done